## Ground Floor
SR. No | Descrptions | Door Code | Size (Actual) | Size (At Site) | Remarks
1 | Entrance Lobby (L00-002) | GD2 | 1500*2400 | Work Balance |  | OK
2 | Corridor (L00-003) | FD9 | 1200*2400 | Work Balance |  | Rectification Required
|  | FD9c | 1200*2400 | Work Balance |  | Woirk Balance
|  | FD11 | 1000*2400 | Work Balance
| FPS SHAFT (00-SH-501) | SD3 | 1000*2100 | 1020*2400 | Sill Work Balance
| HVAC Shaft (00-SH-205) | SD5 | 600*1500 | 600*1470
| HVAC Shaft (00-SH-203) | SD5 | 600*1500 | 600*1490
| FPS SHAFT (00-SH-503) | SD3 | 1000*2100 | Work Balance
3 | Passenger Lift Lobby (L00-004) | FD10 | 1200*2400 | 1240*2500
4 | Unisex Toilet (L00-005) | SD2 | 900*2400 | 900*2400
| PHE SHAFT (00-SH-102) | SD4 | 600*1800 | 580*1800
5 | Security Room / Fire Command Room (L00-006) | GD1 | 1000*2400 | 1000*2401
| Electrical Shaft (00-SH-315) | FD14 | 750*1500 | 750*1490
6 | Accessible Toilet (L00-007) |  |  |  | Size Not Mentioned
7 | SER Room (L00-008) | FD10 | 1200*2400 | 1200*2430
| ELV SHAFT (00-SH-401) | FD14 | 750*1500 | 750*1500
8 | MV Authority Room Source 1 (L00-009) | FD11 | 1000*2400 | 1010*2430
9 | MV Authority Room Source 1 (L00-010) | FD11 | 1000*2400 | 1020*2410
10 | DG Room 1 (L00-011) | FD13 | 1000*2100 | 1020*2110
11 | DG Room 2 (L00-012) | FD13 | 1000*2100 | 1020*2101
|  | AD2 | 1500*2400
12 | DG Room 3 (L00-013) | FD13 | 1000*2100 | 1040*2110
|  | AD2 | 1500*2400
13 | DG Room 4 (L00-014) | AD1 | 2000*2400 | Work Balance
|  | FD13 | 1000*2100 | 1000*2100
14 | DG Room 5 (L00-015) | AD2 | 1500*2400 | Work Balance
|  | FD13 | 1000*2100 | 990*2100
15 | DG Room 6 (L00-016) | AD2 | 1500*2400 | Work Balance
|  | FD13 | 1000*2100 | 1030*2100
16 | DG Room 7 (L00-017) | AD2 | 1500*2400 | Work Balance
|  | FD13 | 1000*2100 | 930*2100
17 | Cylinder Room (L00-018) | FD10 | 1200*2400 | 1190*2480
| HVAC SHAFT (00-SH-206) | SD5 | 600*1500 | Work Balance
| Electrical SHAFT (00-SH-331) | FD14 | 750*1500 | Work Balance
18 | Shipping and Receiving Area (L00-019) | FD11 | 1000*2400 | Work Balance
| FPS SHAFT (00-SH-502) | SD3 | 1000*2100 | 700*2200
| HVAC SHAFT (00-SH-209) | SD3a | 1000*2100 | 990*2200
19 | LD office (L00-020) | SD1 | 1000*2400 | Work Balance
| ELV SHAFT SHAFT (00-SH-402) | FD14 | 750*1500 | 770*1520
20 | Staircase 1 (L00-021) | FD9 | 1200*2400 | 1170*2450
|  | FD9c | 1200*2400 | 1160*2470
21 | Staircase 2 (L00-022) | FD9c | 1200*2400 | 1200*2400
|  | FD9 | 1200*2400 | Work Balance
|  | FD9 | 1200*2400 | Work Balance
22 | Loading/Unloading Area (L00-026)
| PHE SHAFT (00-SH-103) | SD5 | 600*1500 | 600*1520
| Electrical SHAFT (00-SH-345) | FD14 | 750*1500 | Work Balance
| Electrical SHAFT (00-SH-346) | FD14 | 750*1500 | Work Balance
| Electrical SHAFT (00-SH-347) | FD14 | 750*1500 | Work Balance
23 | Hot Air Chamber (L00-027) |  |  |  | Size Not Mentioned
| Security (L00-028) | SD1 | 1000*2400 | Work Balance
|  | SD2a | 900*2400 | Work Balance
24 | Hot Air Chamber & Equipment Access (L00-030) | FD10 | 1200*2400 | Work Balance
| PHE SHAFT (00-SH-101) | SD4 | 600*1800 | Work Balance
25 | Corridor (L00-031) | AD1 | 2100*2400 | Work Balance
26 | Corridor 2 (L00-032) | SD1 | 1000*2400 | Work Balance
|  | SD1 | 1000*2400 | Work Balance
27 | Unisex Toilet 2 (L00-033) | SD2 | 900*2400 | Work Balance
28 | Waste Segregation Room (L00-034) | FD10 | 1200*2400 | Work Balance
|  | FD10 | 1200*2400 | Work Balance
29 | Store Room (L00-035) | FD10 | 1200*2400 | Work Balance
30 | Corridor (L00-036) |  |  | Work Balance
31 | Electrical SHAFT (00-SH-344) | FD14 | 750*1500 | Work Balance

## 1st Floor
SR. No | Descrptions | Door Code | Size (Actual) | Size (At Site)
1 | Passenger Lift Lobby (L01-001) | FD10 | 1200*2400 | 1200*2400 | OK
2 | Corridor (L01-002) |  |  |  | Rectification Required
| FPS SHAFT (01-SH-503) | SD3 | 1000*2100 | 1000*2100 | Woirk Balance
3 | Meeting Room 1 (L01-003) | GD1 | 1000*2400 | Work Balance
4 | Operations Office 2 (L01-004) | GD1 | 1000*2400 | 1000*2430
5 | Meeting Room 3 (L01-005) | GD1 | 1000*2400 | Work Balance
6 | Conference Room (L01-006) | SD1 | 1000*2100 | 1000*2100
| Electrical Shaft (01-SH-314) | FD14 | 750*1500
| Electrical SHAFT (01-SH-315) | FD14 | 750*1500
7 | AHU Room (L01-007) | FD8 | 1500*2400 | 1450*2400
8 | AHU Room 2 (L01-008) | FD8 | 1500*2400 | Work Balance
| Electrical SHAFT (01-SH-304) | FD14 | 750*1500 | 750*1500
9 | Ladies Toilet (L01-009) | SD2 | 900*2400 | 900*2780
10 | Gents Toilet (L01-011) | SD2 | 900*2400 | 940*2780
11 | Ablution Space (L01-012)
12 | Janitor (L01-013) | SD2 | 900*2400 | Work Balance
| Swing 1 Transformer Room (L01-014) | FD3 | 1500*2800 | Work Balance
|  | FD11 | 1000*2400 | 990*2400
| Electrical SHAFT (01-SH-331) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-334) | FD14 | 750*1500 | 750*1500
13 | Swing 2 Transformer Room (L01-015) | FD3 | 1500*2800 | 1500*2800
|  | FD11 | 1000*2400 | Work Balance
| Electrical SHAFT (01-SH-316) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-317) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-318) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-319) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-320) | FD14 | 750*1500 | Work Balance
14 | MV Room Source A (L01-016) | FD8 | 1500*2400 | Work Balance
|  | FD11 | 1000*2400 | 1000*2430
| Electrical SHAFT (01-SH-305) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-306) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-307) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-309) | FD14 | 750*1500 | 750*1500
15 | MV Room Source B (L01-017) | FD8 | 1500*2400 | 1500*2430
|  | FD11 | 1000*2400 | 940*2430
| Electrical SHAFT (01-SH-310) | FD14 | 750*1500 | 740*1500
| Electrical SHAFT (01-SH-311) | FD14 | 750*1500 | 740*1500
| Electrical SHAFT (01-SH-312) | FD14 | 750*1500 | 720*1500
16 | Battery Room 1 (L01-018) | FD10 | 1200*2400 | 1160*2400
17 | Battery Room 1 (L01-019) | FD10 | 1200*2400 | 1140*2400
18 | Shredder Room (L01-021) | FD10 | 1200*2400 | 1180*2400
19 | SOC/NOC Room (L01-022) | GD1 | 1000*2400 | 1130*2400
20 | House Electrical Room Source A (L01-023) | FD3 | 1500*2800 | Work Balance
21 | House Electrical Room Source A (L01-024) | FD3 | 1500*2800 | Work Balance
22 | BMS Room (L01-025) | SD1 | 1000*2400 | 1000*2400
| Electrical SHAFT (01-SH-314) | FD14 | 750*1500 | 750*1500
23 | Female Prayer Room (L01-026) | SD1 | 1000*2400 | Work Balance
24 | Male Prayer Room (L01-027) | SD1 | 1000*2400 | Work Balance
25 | MMR Room 1 (L01-028) | FD4 | 1200*2800 | 1300*2400
| HVAC Shaft (02-SH-203) | SD5 | 600*1500 | 700*1500
| ELV Shaft (02-SH-401) | FD14 | 750*1500 | 740*1500
26 | MMR Room 2 (L01-029) | FD4 | 1200*2800 | Work Balance
| ELV Shaft (02-SH-402) | FD14 | 750*1500 | 750*1500
27 | MSER Room 1 (L01-030) | FD4 | 1200*2800 | Work Balance
| PHE SHAFT (01-SH-103) | SD4 | 600*1800 | 580*1500
| Electrica SHAFT (01-SH-322) | FD14 | 750*1500 | 740*1500
28 | MSER Room 2 (L01-031) | FD4 | 1200*2800 | 1200*2800
29 | Store Room 1 (L01-032) | SD7 | 1200*2800 | 1170*2800
30 | Store Room 2 (L01-033) | SD7 | 1200*2800 | 1180*2800
31 | Store Room 3 (L01-034) | SD7 | 1200*2800 | 1170*2800
32 | Staircase 1 (L01-035) | FD9b | 1200*2200 | 1150*2300
33 | Staircase 2 (L01-036) | FD9a | 1200*2200 | 1200*2200
34 | Cafeteria (L01-040) | GD2 | 1495*2375 | Work Balance
35 | Managers Office (L01-041) | GD1 | 1000*2400 | Work Balance
36 | Operations Office (L01-042) | GD1 | 1000*2400 | Work Balance
|  | GD1 | 1000*2400 | Work Balance
| HVAC SHAFT (01-SH-201) | SD5 | 600*1500 | 580*1500
37 | Cylinder Room (L01-043) | FD10 | 1200*2400 | 1220*2400
| Electrical SHAFT (01-SH-323) | FD15 | 600*1500 | 600*1500
| Electrical SHAFT (01-SH-324) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-325) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-326) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-327) | FD14 | 750*1500 | 750*1500
38 | Waiting Area (L01-044)
| FPS SHAFT (01-SH-501) | SD3 | 1000*2100 | 990*2090
39 | Corridor (L01-045) | FD8 | 1500*2400 | 1470*2400
| HVAC SHAFT (01-SH-209) | SD3 | 1000*2100 | 1000*2100
| Electrical SHAFT (01-SH-336) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-337) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-338) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (01-SH-339) | FD15 | 600*1500 | 640*1480
| FPS SHAFT (01-SH-501) | SD3 | 1000*2100 | 1000*2100

## 2nd Floor
SR. No | Descrptions | Door Code | Size (Actual) | Size (At Site)
1 | Passenger Lift Lobby (L02-001) | FD12 | 1200*2400 | 1160*2480 |  | OK
2 | Corridor (L02-002) | FD12 | 1200*2400 | 1200*2460 |  | Rectification Required
| HVAC Shaft (00-SH-205) | SD5 | 600*1500 | 600*1500 |  | Woirk Balance
| HVAC Shaft (00-SH-206) | SD6 | 600*1200 | 630*1220
| HVAC Shaft (00-SH-208) | SD5 | 600*1500 | Work Balance
| HVAC Shaft (00-SH-209) | SD3a | 1000*2100 | 1000*2100
| HVAC Shaft (00-SH-210) | SD6 | 600*1200 | 580*1230
| Electrical Shaft (00-SH-313) | FD14 | 750*1500 | 750*1500
| FPS SHAFT (00-SH-501) | SD3 | 1000*2100 | 1000*2160
| FPS SHAFT (00-SH-502) | SD3 | 1000*2100 | 1000*2100
| FPS SHAFT (00-SH-503) | SD3 | 1000*2100 | 1000*2300
3 | Man Trap (L02-003) | FD12 | 1200*2400 | 1200*2540
4 | Unisex Toilet (L02-004) | SD2 | 900*2400 | 1200*2470
| PHE Shaft (00-SH-102) | SD4 | 600*1800 | 590*1900
5 | IT 1 Battery Room Source A (L02-005) | FD10 | 1200*2400 | 1175*2400
6 | IT 1 Battery Room Source B (L02-006) | FD10 | 1200*2400 | 1170*2400
7 | IT Electrical Room Source A (L02-007) | FD1 | 2000*2800 | 1950*2800
|  | FD11 | 1000*2400 | 1000*2400
| HVAC Shaft (02-SH-201) | FD15 | 600*1500 | Work Balance
| Electrical SHAFT (02-SH-331) | FD14 | 750*1500 | 760*1650
| Electrical SHAFT (02-SH-332) | FD14 | 750*1500 | 770*1670
| Electrical SHAFT (02-SH-333) | FD14 | 750*1500 | 770*1670
| Electrical SHAFT (02-SH-334) | FD14 | 750*1500 | 780*1670
| Electrical SHAFT (02-SH-335) | FD14 | 750*1500 | 770*1670
| Electrical SHAFT (02-SH-336) | FD14 | 750*1500 | 770*1670
| Electrical SHAFT (02-SH-337) | FD14 | 750*1500 | 750*1670
| Electrical SHAFT (02-SH-338) | FD14 | 750*1500 | 750*1680
8 | IT 1 Electrical Room Source B (L02-008) | FD1 | 2000*2800 | 2000*3000
|  | FD11 | 1000*2400 | Work Balance | MS Fixing not done properly
| HVAC Shaft (02-SH-207) | FD15 | 600*1500 | 630*1500
| Electrical SHAFT (02-SH-314) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (02-SH-315) | FD14 | 750*1500 | 770*1500
| Electrical SHAFT (02-SH-316) | FD14 | 750*1500 | 790*1530
| Electrical SHAFT (02-SH-317) | FD14 | 750*1500 | 770*1500
| Electrical SHAFT (02-SH-318) | FD14 | 750*1500 | 770*1500
| Electrical SHAFT (02-SH-319) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (02-SH-320) | FD14 | 750*1500 | 790*1500
| Electrical SHAFT (02-SH-321) | FD15 | 600*1500 | 600*1500
9 | IT 1 Transfer Room (L02-009) | FD2 | 1800*2800 | Work Balance
|  | FD11 | 1000*2400 | 1000*2400
| PHE Shaft (02-SH-101) | FD15 | 600*1500 | 620*1680
| Electrical Shaft (02-SH-303) | FD15 | 600*1500 | 630*1660
| Electrical SHAFT (02-SH-304) | FD14 | 750*1500 | Work Balance
| Electrical SHAFT (02-SH-307) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (02-SH-308) | FD14 | 750*1500 | 780*1500
10 | MMR Room 1 (L02-010) | FD4 | 1200*2800 | 1180*2950
| HVAC Shaft (02-SH-203) | SD5 | 600*1500 | 600*1500
| ELV Shaft (02-SH-401) | FD14 | 750*1500 | 740*1490
11 | MMR Room 2 (L02-011) | FD4 | 1200*2800 | 1320*2800
| ELV Shaft (02-SH-402) | FD14 | 750*1500 | 780*1500
12 | SER Room 1 (L02-012) | FD10 | 1200*2400 | 1200*2400
| HVAC Shaft (02-SH-202) | SD5 | 600*1500 | 630*1500
| Electrical Shaft (02-SH-301) | FD14 | 750*1500 | 770*1500
13 | SER Room 2 (L02-013) | FD10 | 1200*2400 | 1220*2440
| PHE Shaft (02-SH-103) | SD4 | 600*1800 | 590*1780
14 | Data Hall (L02-014) | FD3 | 1500*2800 | 1500*2770
|  | FD3 | 1500*2800 | 1470*2800
15 | FWU Gallery 1 (L02-015) | FD1 | 2000*2800 | 2000*2770
|  | FD11 | 1000*2400 | 1000*2400
16 | FWU Gallery 2 (L02-016) | FD1 | 2000*2800 | 2000*2800
|  | FD11 | 1000*2400 | 990*2400
16 | Staircase 1 (L02-017) | FD9 | 1200*2400 | 1160*2480
17 | Staircase 2 (L02-018) | FD9 | 1200*2400 | 1190*2400
18 | Cylinder Room (L02-022) | FD10 | 1200*2400 | 1200*2400
| Electrical SHAFT (02-SH-323) | FD15 | 600*1500 | 630*1470
| Electrical SHAFT (02-SH-326) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (02-SH-327) | FD14 | 750*1500 | Work Balance
19 | Store Room (L02-023) | SD1 | 1000*2400 | 1000*2400
| Electrical SHAFT (02-SH-310) | FD14 | 750*1500 | 790*1700
| Electrical SHAFT (02-SH-311) | FD14 | 750*1500 | 790*1700
20 | Store Room 2 (L02-024) | SD1 | 1000*2400 | 1000*2400

## 3rd Floor
SR. No | Descrptions | Door Code | Size (Actual) | Size (At Site)
1 | Passenger Lift Lobby (L03-001) | FD12 | 1200*2400 | 1220*2550 | OK
2 | Corridor (L03-002) | FD12 | 1200*2400 | 1240*2400 | Rectification Required
| HVAC Shaft (03-SH-205) | SD6 | 600*1200 | 570*1200 | Woirk Balance
| HVAC Shaft (03-SH-206) | SD6 | 600*1200 | 600*1180
| HVAC Shaft (03-SH-208) | SD5 | 600*1500 | 590*1500
| HVAC Shaft (03-SH-209) | SD3a | 1000*2100 | 1000*2100
| HVAC Shaft (03-SH-210) | SD6 | 600*1200 | 600*1500
| Electrical Shaft (03-SH-313) | FD14 | 750*1500 | 740*1490
| FPS SHAFT (03-SH-501) | SD3 | 1000*2100 | Work Balance
| FPS SHAFT (03-SH-502) | SD3 | 1000*2100 | 1000*2100
| FPS SHAFT (03-SH-503) | SD3 | 1000*2100 | 1000*2100
3 | Man Trap (L03-003) | FD12 | 1200*2400 | 1220*2550
4 | Unisex Toilet (L03-004) | SD2 | 900*2400 | 880*2400
| PHE Shaft (00-SH-102) | SD4 | 600*1800 | 600*1850
5 | IT 1 Battery Room Source A (L03-005) | FD10 | 1200*2400 | 1160*2400
6 | IT 1 Battery Room Source B (L03-006) | FD10 | 1200*2400 | 1180*2400
7 | IT Electrical Room Source A (L03-007) | FD1 | 2000*2800 | 1960*2820
|  | FD11 | 1000*2400 | 1030*2420
| HVAC Shaft (03-SH-201) | FD15 | 600*1500 | Work Balance
| Electrical SHAFT (03-SH-331) | FD14 | 750*1500 | 770*1480
| Electrical SHAFT (03-SH-332) | FD14 | 750*1500 | 770*1480
| Electrical SHAFT (03-SH-333) | FD14 | 750*1500 | 730*1500
| Electrical SHAFT (03-SH-334) | FD14 | 750*1500 | 770*1500
| Electrical SHAFT (03-SH-335) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (03-SH-336) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (03-SH-337) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (03-SH-338) | FD14 | 750*1500 | 750*1500
8 | IT 1 Electrical Room Source B (L03-008) | FD1 | 2000*2800 | 1980*2800
|  | FD11 | 1000*2400 | 1000*2430
| HVAC Shaft (03-SH-207) | FD15 | 600*1500 | 600*1500
| Electrical SHAFT (03-SH-314) | FD14 | 750*1500 | Work Balance
| Electrical SHAFT (03-SH-315) | FD14 | 750*1500 | Work Balance
| Electrical SHAFT (03-SH-316) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (03-SH-317) | FD14 | 750*1500 | 740*1500
| Electrical SHAFT (03-SH-318) | FD14 | 750*1500 | 770*1500
| Electrical SHAFT (03-SH-319) | FD14 | 750*1500 | 740*1500
| Electrical SHAFT (03-SH-320) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (03-SH-321) | FD14 | 750*1500 | 770*1500
9 | IT 2 Transfer Room (L03-009) | FD2 | 1800*2800 | Work Balance
|  | FD11 | 1000*2400 | 1000*2940
| PHE Shaft (03-SH-101) | FD15 | 600*1500 | 620*1500
| Electrical Shaft (02-SH-302) | FD15 | 600*1500 | 600*1500
| Electrical Shaft (02-SH-303) | FD14 | 750*1500 | 770*1500
| Electrical SHAFT (02-SH-304) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (02-SH-305) | FD14 | 750*1500 | 770*1500
| Electrical SHAFT (02-SH-306) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (02-SH-307) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (02-SH-308) | FD14 | 750*1500 | 750*1660
| Electrical SHAFT (02-SH-309) | FD14 | 750*1500 | 750*1670
10 | MMR Room 1 (L03-010) | FD4 | 1200*2800 | 1200*2400
| HVAC Shaft (03-SH-203) | SD5 | 600*1500 | 590*1500
| ELV Shaft (03-SH-401) | FD14 | 750*1500 | 750*1500
11 | MMR Room 2 (L03-011) | FD4 | 1200*2800 | 1350*2800
| ELV Shaft (03-SH-402) | FD14 | 750*1500 | 770*1500
12 | SER Room 1 (L03-012) | FD10 | 1200*2400 | 1200*2400
| HVAC Shaft (03-SH-202) | SD5 | 600*1500 | 620*1500
| Electrical Shaft (03-SH-301) | FD14 | 750*1500 | 770*1501
13 | SER Room 2 (L03-013) | FD10 | 1200*2400 | 1200*2400
| PHE Shaft (03-SH-103) | SD4 | 600*1800 | 600*1800
| Electrical SHAFT (03-SH-322) | FD14 | 750*1500 | 760*1500
14 | Data Hall (L03-014) | FD3 | 1500*2800 | 1470*2800
|  | FD3 | 1500*2800 | 1480*2800
15 | FWU Gallery 1 (L03-015) | FD1 | 2000*2800 | 2060*2800
|  | FD11 | 1000*2400 | 1000*2470
16 | FWU Gallery 2 (L03-016) | FD1 | 2000*2800 | 2000*2800
|  | FD11 | 1000*2400 | 1000*2400
16 | Staircase 1 (L03-017) | FD9 | 1200*2400 | 1190*2480
17 | Staircase 2 (L03-018) | FD9 | 1200*2400 | 1190*2480
18 | Cylinder Room (L03-022) | FD10 | 1200*2400 | Work Balance
| Electrical SHAFT (03-SH-323) | FD15 | 600*1500 | Work Balance
| Electrical SHAFT (03-SH-324) | FD14 | 750*1500 | Work Balance
| Electrical SHAFT (03-SH-325) | FD14 | 750*1500 | Work Balance
| Electrical SHAFT (03-SH-326) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (03-SH-327) | FD14 | 750*1500 | 750*1500
19 | Store Room (L03-023) | SD7 | 1200*2800 | 1000*2940
| Electrical SHAFT (03-SH-310) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (03-SH-311) | FD14 | 750*1500 | 750*1490
20 | Store Room 2 (L03-024) | SD7 | 1200*2800 | 1030*2950
| Electrical SHAFT (03-SH-312) | FD14 | 750*1500 | 750*1500

## 4th Floor
SR. No | Descrptions | Door Code | Size (Actual) | Size (At Site)
1 | Passenger Lift Lobby (L04-001) | FD12 | 1200*2400 | 1180*2480 | OK
2 | Corridor (L04-002) | FD12 | 1200*2400 | 1200*2900 | Rectification Required
| HVAC Shaft (04-SH-205) | SD6 | 600*1200 | 660*1220 | Woirk Balance
| HVAC Shaft (04-SH-206) | SD6 | 600*1200 | 600*1470
| HVAC Shaft (04-SH-208) | SD5 | 600*1500 | 630*1570
| HVAC Shaft (04-SH-209) | SD3a | 1000*2100 | 1000*2100
| HVAC Shaft (04-SH-210) | SD6 | 600*1200 | 590*1190
| Electrical Shaft (04-SH-313) | FD14 | 750*1500 | 780*1500
| FPS SHAFT (04-SH-501) | SD3 | 1000*2100 | Work Balance
| FPS SHAFT (04-SH-502) | SD3 | 1000*2100 | 1000*2100
| FPS SHAFT (04-SH-503) | SD3 | 1000*2100 | 970*2100
3 | Man Trap (L04-003) | FD12 | 1200*2400 | 1190*2520
4 | Unisex Toilet (L04-004) | SD2 | 900*2400 | 1080*2420
| PHE Shaft (04-SH-102) | SD4 | 600*1800 | 620*1920
5 | IT 3 Battery Room Source A (L04-005) | FD10 | 1200*2400 | 1180*2430
6 | IT 3 Battery Room Source B (L04-006) | FD10 | 1200*2400 | 1130*2410
7 | IT Electrical Room Source A (L04-007) | FD1 | 2000*2800 | 1950*2820
|  | FD11 | 1000*2400 | 1030*2420
| HVAC Shaft (04-SH-201) | FD15 | 600*1500 | 590*1520
| Electrical SHAFT (04-SH-331) | FD14 | 750*1500 | 740*1500
| Electrical SHAFT (04-SH-332) | FD14 | 750*1500 | 750*1500
| Electrical SHAFT (04-SH-333) | FD14 | 750*1500 | 740*1500
| Electrical SHAFT (04-SH-334) | FD14 | 750*1500 | 730*1500
| Electrical SHAFT (04-SH-335) | FD14 | 750*1500 | 740*1500
| Electrical SHAFT (04-SH-336) | FD14 | 750*1500 | 730*1500
| Electrical SHAFT (04-SH-337) | FD14 | 750*1500 | 730*1500
| Electrical SHAFT (04-SH-338) | FD14 | 750*1500 | 750*1500
8 | IT 3 Electrical Room Source B (L04-008) | FD1 | 2000*2800 | 1950*2800
|  | FD11 | 1000*2400 | 950*2410
| HVAC Shaft (04-SH-207) | FD15 | 600*1500 | 740*1500
| Electrical SHAFT (04-SH-314) | FD14 | 750*1500 | Work Balance
| Electrical SHAFT (04-SH-315) | FD14 | 750*1500 | Work Balance
| Electrical SHAFT (04-SH-316) | FD14 | 750*1500 | 720*1500
| Electrical SHAFT (04-SH-317) | FD14 | 750*1500 | 740*1500
| Electrical SHAFT (04-SH-318) | FD14 | 750*1500 | 740*1500
| Electrical SHAFT (04-SH-319) | FD14 | 750*1500 | 730*1500
| Electrical SHAFT (04-SH-320) | FD14 | 750*1500 | 740*1500
| Electrical SHAFT (04-SH-321) | FD14 | 750*1500 | 740*1500
9 | IT 3 Transfer Room (L04-009) | FD2 | 1800*2800 | Work Balance
|  | FD11 | 1000*2400 | 1000*2400
| PHE Shaft (04-SH-101) | FD15 | 600*1500 | 630*1520
| Electrical Shaft (04-SH-303) | FD15 | 600*1500 | 630*1520
| Electrical SHAFT (04-SH-304) | FD14 | 750*1500 | Work Balance
| Electrical SHAFT (04-SH-307) | FD14 | 750*1500 | 750*1530
| Electrical SHAFT (04-SH-308) | FD14 | 750*1500 | 730*1530
10 | MMR Room 1 (L04-010) | FD4 | 1200*2800 | 1220*2880
| HVAC Shaft (04-SH-203) | SD5 | 600*1500 | 630*1530
| ELV Shaft (04-SH-401) | FD14 | 750*1500 | 750*1500
11 | MMR Room 2 (L04-011) | FD4 | 1200*2800 | 1340*2810
| ELV Shaft (04-SH-402) | FD14 | 750*1500 | 740*1520
12 | SER Room 1 (L04-012) | FD10 | 1200*2400 | 1340*2400
| HVAC Shaft (04-SH-202) | SD5 | 600*1500 | 700*1500
| Electrical Shaft (04-SH-301) | FD14 | 750*1500 | 770*1501
13 | SER Room 2 (L04-013) | FD10 | 1200*2400 | 1220*2420
| PHE Shaft (04-SH-103) | SD4 | 600*1800 | Work Balance
14 | Data Hall (L04-014) | FD3 | 1500*2800 | 1500*2800
|  | FD3 | 1500*2800 | 1450*2810
15 | FWU Gallery 1 (L04-015) | FD1 | 2000*2800 | 2020*2810
|  | FD11 | 1000*2400 | 1130*2400
16 | FWU Gallery 2 (L04-016) | FD1 | 2000*2800 | 2000*2800
|  | FD11 | 1000*2400 | 1020*2420
16 | Staircase 1 (L04-017) | FD9 | 1200*2400 | 1180*2480
17 | Staircase 2 (L04-018) | FD9 | 1200*2400 | 1210*2380
18 | Cylinder Room (L04-022) | FD10 | 1200*2400 | 1240*2400
| Electrical SHAFT (04-SH-323) | FD15 | 600*1500 | 570*1500
| Electrical SHAFT (04-SH-326) | FD14 | 750*1500 | 740*1500
| Electrical SHAFT (04-SH-327) | FD14 | 750*1500 | 730*1490
19 | APFCR Room (L04-023) | FD11 | 1000*2400 | 1030*2430
| Electrical SHAFT (04-SH-310) | FD14 | 750*1500 | 780*1510
20 | APFCR Room 2 (L04-024) | FD11 | 1000*2400 | 1040*2400
| Electrical SHAFT (03-SH-311) | FD14 | 750*1500 | 790*1520
21 | APFCR Room 3 (L04-024) | FD11 | 1000*2400 | 1000*2400
22 | Store Room (L04-024) | SD1 | 1000*2400 | 1000*2400